## action
Action type | Action | Remark | PIC | Cut-off | Status | Data source
Project Settings | Requirements & Architecture | Tech stack finalized: React + FastAPI + Azure SQL + Fabric Lakehouse | Jakkarit | 17-Apr-26 | Done
Project Settings | Azure SQL DB Setup | DB server created, firewall configured, 5 tables created (budget_submissions, approval_status, etc.) | Jakkarit | 24-Apr-26 | Done
Project Settings | Azure Container Registry | cmanbudgetacr.azurecr.io — Basic tier, Southeast Asia | Jakkarit | 24-Apr-26 | Done
Project Settings | Azure Container Apps | cman-budget-mngt-web created with Log Analytics workspace | Jakkarit | 24-Apr-26 | Done
Project Settings | Fabric Workspace + Lakehouse + Notebooks | Workspace: budget_management_web — nb_upload_actuals, nb_send_email created | Jakkarit | 24-Apr-26 | Done
Data Pipeline | mas_employee_data Sync Script | C-POP HR API → Azure SQL, incremental sync (setup/sync_employees.py), 621 Active employees | Jakkarit | 5-May-26 | Done
Data Pipeline | GitHub Actions Daily Sync | 06:00 Bangkok daily (.github/workflows/sync_employees.yml), first run verified 2026-05-05 | Jakkarit | 5-May-26 | Done
Data Pipeline | dim_cost_center Analysis | Source: docs/Cost center (Update 18 Mar 26) 1.xlsx — 210 rows, orgcode join strategy identified | Jakkarit | 6-May-26 | Done
Data Pipeline | Verify orgcode → Cost Center Link | Confirmed: orgcode (C-POP format e.g. 1165403) != SAP CC format (e.g. 10IT011100) — bridge table dim_orgcode_costcenter_map required, data from Chatdanai API | Jakkarit | 15-May-26 | Done
Data Pipeline | sap_m_cost_center Table | Cost center reference table already exists in system as sap_m_cost_center — no need to create dim_cost_center | Jakkarit | 6-May-26 | Done
Development | Project Folder Restructure | Create backend/ + frontend/ folder structure per architecture plan | Jakkarit | 13-May-26 | In Progress
Development | FastAPI Backend | main.py + routers: /api/auth, /api/budget, /api/approval, /api/dashboard, /api/admin | Jakkarit | 13-May-26 | In Progress
Development | React + Vite Frontend Scaffold | Pages: Login, Submit Budget (Template 1.1), Approve (VP/Staff/Manager), Dashboard, Admin | Jakkarit | 13-May-26 | In Progress
Data Pipeline | SAP Gap Columns — Ticket to SAP Team | Add 4 cols to sap_t_gl_trans: Entry Date, Order, Object Class, Order Short Text. Ratima สร้าง SAP_T_GL_TRANS_1000_RATIMA_TEST1 เสร็จแล้ว — กำลังตรวจสอบข้อมูลในไฟล์ | Ratima | 13-May-26 | In Progress
Data Pipeline | SAP_M_INTERNAL_ORDER | Cancelled — user not use | Ratima | 13-May-26 | Done
Project Action | Meeting with User — Template Filling Data | Discuss how users fill budget template data, confirm workflow and UX requirements | Jakkarit | 13-May-26 | Done
Data Pipeline | Cost Center -> Line Officer Link | Chatdanai investigating how dim_cost_center links to line officers via empcode — currently in testing | Chatdanai | 13-May-26 | In Progress
Development | Weekly Update Skill | Created skill/skill_weekly_update.md + upgraded create_weekly_update.py to merge SP tasks before upload | Jakkarit | 6-May-26 | Done
Data Pipeline | SAP Job Run Setup | If SAP_M_INTERNAL_ORDER + SAP_T_GL_TRANS_1000_RATIMA_TEST1 test pass, data OK → Jakkarit แจ้งกลับ SAP Team เพื่อตั้ง Scheduled Job Run ใน SAP Production | Jakkarit | 13-May-26 | In Progress
Project Action | 1st Recap Project with Laddawan | นัด recap ความคืบหน้าโปรเจกต์ครั้งแรก Thu 14/05/2026 8:30-9:00 AM — ยิง MS Teams invite แล้ว | Jakkarit | 14-May-26 | Done
Data Pipeline | OneLake Connection | cman-fabric-write added to workspace, setup/connect_onelake.py created, connection verified | Jakkarit | 07-May-26 | Done
Data Pipeline | On-premises Gateway | cman-dw-dev-conn-gateway created on E-SMARTISO server, Fabric Data Pipeline: D:/SAPDW/PRD -> Files/00landing configured | Jakkarit | 07-May-26 | Done
Data Pipeline | 00landing Files | 3 SAP test files landed: SAP_T_GL_TRANS_1000_RATIMA_TEST1 (233,372 rows/116MB), SAP_M_COST_CENTER (341), SAP_M_INTERNAL_ORDER (2,543) | Jakkarit | 07-May-26 | Done
Data Pipeline | nb_landing_to_bronze | bronze_ACDOCA (233,372), bronze_sap_m_cost_center (341), bronze_sap_m_internal_order (2,543) loaded as Delta tables | Jakkarit | 07-May-26 | Done
Data Pipeline | nb_bronze_to_silver | silver_sap_gl_trans (88 cols, sign-flip on 6 amount/FX cols), silver_cost_center_master, silver_internal_order_master | Jakkarit | 07-May-26 | Done
Data Pipeline | entry_date null issue | SAP date format = yyyyMMdd (no dash) — fixed sc() helper to use to_date(c, 'yyyyMMdd'), covers all date cols automatically, entry_date verified not null | Jakkarit | 07-May-26 | Done
Data Pipeline | entry_date fix | SAP date format = yyyyMMdd (no dash) — fixed sc() helper to use to_date(c, 'yyyyMMdd'), covers all date cols automatically | Jakkarit | 07-May-26 | Done
Data Pipeline | Bronze->Silver Data Consistency Check | Verify no data loss after transform: null counts per col, row counts match, date cols parse correctly, amount sign-flip correct | Jakkarit | 08-May-26 | In Progress
Data Pipeline | Cost Type Master — cost_type & cost_sub_type | Added cost_type + cost_sub_type cols to docs/cost type master.xlsx: GL5→Indirect, GL6+10SC012000→Logistic/Admin, GL6+10CM*/10SC*(≠10SC012000)→SGA/Selling, GL6 others→SGA/Admin | Jakkarit | 13-May-26 | Done
Development | Landing Page Design | Design step: landing page based on docs/index.html (Chememan branding, dark/light theme, glassmorphism) — not yet built | Jakkarit | TBC | In Progress
Development | Module 1 — Import/Export Approved Budget | Design step: budget dept export approved_budget_{yyyy}.csv (15 cols), import with validation, overwrite-by-year, near-realtime table — not yet built | Jakkarit | TBC | In Progress
Project Action | Meeting with User — Special Template Phase 2 | Discuss special template requirements (phase 2) — confirm workflow and UX for special cases | Jakkarit | TBC | In Progress
Data Pipeline | Cost Center -> Line Officer Link (Chatdanai API) | Need API: orgcode → cost_center mapping. API structure to request: empcode, primary_orgcode, primary_costcenter, all_positions[] | Chatdanai | TBC | In Progress
Development | Budget Form UX Design Analysis | CC hierarchy verified (210 CC→109 dept→38 div). 1 user=1 dept fills all CCs. GL dropdown by actuals history per CC (not 52/62 prefix rule). User does 3 things: select CC, select GL, enter Jan-Dec. | Jakkarit | TBC | In Progress
Data Pipeline | dim_costcenter_division_map | Create table in Azure SQL, load 210 rows from 02cost center & department (master).xlsx — cost_center→division+department mapping | Jakkarit | TBC | In Progress
Data Pipeline | dim_orgcode_costcenter_map | Create table in Azure SQL — orgcode→cost_center bridge. Source: file from DW project (same source Chatdanai's team uses), not API. Need file path from DW project. | Jakkarit | TBC | In Progress
Data Pipeline | dim_gl_master | Create table in Azure SQL, load 137 rows from 04gl code & gl group & gl thai name (master).xlsx — gl_account→group_exp+thai_name | Jakkarit | TBC | In Progress